## How to Use
PROJECT MANAGEMENT — GANTT CHART TEMPLATE
Quick Start
1. | Go to the "Gantt" sheet.
2. | Set the Project Start Date in the yellow cell (B2). Use a MONDAY for clean week alignment.
3. | For each task, fill in: Task name • Owner • Start Date • End Date • % Done • Project Update
4. | Everything else is automatic — Duration, Status, Gantt bar, and the KPI summary at the top all update by themselves.
KPI Summary (rows 3-4)
TOTAL ACTION | Counts all rows where a Start Date is filled (section headers excluded).
OPEN | Tasks with status = Planned (0% done, not yet started).
IN PROGRESS | Tasks currently being worked on (% Done between 0 and 100).
DONE | Tasks with % Done = 100%.
DELAYED | Tasks past their End Date but not yet 100% complete.
% COMPLETION | Average % Done across all real tasks — overall project progress.
Status Colors (automatic)
🟩 GREEN | Done — when % Done = 100%
🟦 BLUE | In Progress — when 0% < % Done < 100% and End Date ≥ today
🟥 RED | Delayed — when End Date < today AND % Done < 100%
⬜ GRAY | Planned — when % Done = 0% and End Date ≥ today
🟨 YELLOW | Vertical band marks the current week (TODAY)
Adjusting Week Columns
• | Shift all weeks: change the Project Start Date in cell B2.
• | Show fewer weeks: right-click the unwanted week columns → Hide.
• | Add more weeks: select the last week column, copy it, and paste to the right.
• | Week labels (WK01, WK02, …) are calculated from the date in row 6 — do not type over them.
Adding / Removing Tasks
• | 40 task rows are pre-formatted. Just type into the next empty row.
• | For a section header (like "1. PLANNING"), type the name only — leave Start/End/% Done empty.
• | To add more rows: select an existing task row, right-click → Insert. Formulas copy automatically.
Color Code for Cells
🟨 Yellow | Input cells — you can type here.
🔵 Blue text | Hardcoded values you enter (dates, % Done).
⚫ Black text | Formulas — do not overwrite.
Tip | The header row and first 8 columns are frozen — scroll right to see future weeks while still seeing task names.

## Gantt
PROJECT MANAGEMENT — GANTT CHART
Project Start Date (Mon): | 2026-04-08 | Today: | 2026-06-24 |  | Legend: |  |  | Done |  | In Progress |  | Planned |  | Delayed |  | Today
TOTAL ACTION |  | OPEN |  | IN PROGRESS |  | DONE |  | DELAYED |  |  |  | % COMPLETION
58 |  | 10 |  | 9 |  | 32 |  | 7 |  |  |  | 67.59%
Task / Milestone | Owner | Start Date | End Date | Duration (days) | % Done | Status | Project Update | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44
[7 empty] | Week starting → | 2026-04-08 | 2026-04-15 | 2026-04-22 | 2026-04-29 | 2026-05-06 | 2026-05-13 | 2026-05-20 | 2026-05-27 | 2026-06-03 | 2026-06-10 | 2026-06-17 | 2026-06-24 | 2026-07-01 | 2026-07-08 | 2026-07-15 | 2026-07-22 | 2026-07-29 | 2026-08-05 | 2026-08-12 | 2026-08-19 | 2026-08-26 | 2026-09-02 | 2026-09-09 | 2026-09-16 | 2026-09-23 | 2026-09-30 | 2026-10-07 | 2026-10-14 | 2026-10-21 | 2026-10-28
1. PLANNING
Project kick-off meeting | Method/Maintenance | 2026-04-08 | 2026-04-10 | 3 | 100% | Done
Define scope & objectives | Method/Maintenance | 2026-04-08 | 2026-04-10 | 3 | 100% | Done
Resource & budget approval | Bagus/Riky | 2026-04-12 | 2026-04-26 | 15 | 100% | Done
2. EQUIPMENT PROCUREMENT
PO issue – SPEA T100 | Yudha/Sunanto | 2026-04-15 | 2026-04-27 | 13 | 100% | Done
Delivery – SPEA T100 | SPEA/Sunanto | 2026-05-10 | 2026-06-20 | 42 | 100% | Done | Lead time 12 wks; ETA 7 June 2026
PO issue – Comisioning | Sunanto | 2026-04-15 | 2026-04-27 | 13 | 100% | Done | Waiting Eezy Approval
Delivery – Comisioning | Sunanto | 2026-06-20 | 2026-06-30 | 11 | 50% | In Progress
PO issue – Progam Integration | Riky | 2026-05-20 | 2026-06-01 | 13 | 100% | Done | 38 refference Aurora
Delivery – Progam Integration | Riky | 2026-06-20 | 2026-06-30 | 11 | 50% | In Progress
PO issue – New Fixture | Riky | 2026-06-25 | 2026-07-10 | 16 | 50% | In Progress | Wating comfirmation Size required (Specialy for Aurora)
Delivery – New Fixture | Riky | 2026-07-11 | 2026-11-18 | 131 | 0% | Planned
3. EXECUTION
Layout Plan | Riky | 2026-06-01 | 2026-06-05 | 5 | 100% | Done | Option 1 : Add Tester at current Back end Option 2 : Create New Back End
Genba layout during Relay-out | Riky/Bagus | 2026-06-01 | 2026-06-05 | 5 | 100% | Done
Bench Prepparation | Riky | 2026-06-01 | 2026-06-15 | 15 | 100% | Done | Option 1 : use ex Maximo Option 2 : Use ex Kala
PC, Monitor & Printer Preparation | Riky/Sunanto | 2026-06-01 | 2026-06-15 | 15 | 100% | Done | Installation V.S
DB Panel Preparation | Riky | 2026-06-01 | 2026-06-15 | 15 | 100% | Done | Use From Bench KIZOKU
Line Acessories (Quality requirement) | Riky | 2026-06-01 | 2026-06-15 | 15 | 80% | Delayed | ID Line ,ok1st part, Kamishibai, POKAYOKE) follow up with IRWAN
PC LDS | Muktar | 2026-06-01 | 2026-06-15 | 15 | 50% | Delayed | Preppared by Muktar
Assembly Program Integration | Riky/Sunanto | 2026-06-01 | 2026-06-15 | 15 | 50% | Delayed | Create New; Modify PLC panel
ITAC (Process Flow) | Riky | 2026-06-10 | 2026-06-22 | 13 | 100% | Done | Source for ITAC Integration
ITAC (Matrix Material) | Riky | 2026-06-10 | 2026-06-22 | 13 | 100% | Done | Source for ITAC Integration
ITAC (BOM Creation) | Friska | 2026-06-10 | 2026-06-22 | 13 | 100% | Done | Source for ITAC Integration
ITAC (Create Work Plan) | Riky | 2026-06-10 | 2026-06-22 | 13 | 100% | Done | Source for ITAC Integration
ITAC (Set Error Code) | Irwan | 2026-06-10 | 2026-06-22 | 13 | 100% | Done | Source for ITAC Integration
ITAC (Info Text Data Update) | Friska | 2026-06-10 | 2026-06-22 | 13 | 100% | Done | Source for ITAC Integration
Handle Scanner | Riky | 2026-06-10 | 2026-06-22 | 13 | 100% | Done | 3 pcs required
Golden Sample Matrix | Riky | 2026-06-10 | 2026-06-22 | 13 | 100% | Done | Check current Golden sample for Set-up New Tester
UPS for SPEA | Sunanto | 2026-06-10 | 2026-06-22 | 13 | 100% | Done
Nice Label Lisence | Sunanto | 2026-06-10 | 2026-06-22 | 13 | 100% | Done
LAN Integration | Muktar | 2026-06-10 | 2026-06-22 | 13 | 100% | Done | 4 Point
Qualification Plan | Irwan | 2026-06-10 | 2026-06-22 | 13 | 100% | Done | Reffer Aurora at NIJI line (29-05-2026) Considering MAC Address Issue
Antistatique Mate | Riky | 2026-06-10 | 2026-06-22 | 13 | 100% | Done
Pressure Integration | Riky | 2026-06-10 | 2026-06-22 | 13 | 100% | Done | Use Vendor
MPH Set-up | Riky/Nadia | 2026-06-10 | 2026-06-22 | 13 | 30% | Delayed | BIN.SAP. Etc (calculating KB to OFO)
Line Lighting (Center & Bench) | Riky | 2026-06-10 | 2026-06-22 | 13 | 100% | Done | Allready request to Facility to activated
Reject Box (Yellow & Red Box) | Riky | 2026-06-10 | 2026-06-22 | 13 | 100% | Done
AM-PM Set-up | Sunanto | 2026-06-10 | 2026-06-22 | 13 | 0% | Delayed
Stagging U-Disk for SPEA | Riky | 2026-06-10 | 2026-06-22 | 13 | 100% | Done
Pallete Staging AGV | Riky | 2026-06-10 | 2026-06-22 | 13 | 50% | Delayed | Include Set-up AGV
LDS & DIS Set-up | Funny/Bagus | 2026-06-10 | 2026-06-22 | 13 | 0% | Delayed
4. INSTALLATION & SETUP
SPEA T100 installation & cabling | Sunanto / SPEA | 2026-06-10 | 2026-06-30 | 21 | 50% | In Progress | waiting UPS confirmation (original missing UPS
Installation SPEA T100 to current line | Riky | 2026-06-20 | 2026-06-23 | 4 | 100% | Done
SPEA T100 software load & config | SPEA FSE | 2026-06-10 | 2026-06-30 | 21 | 50% | In Progress
Packing Bench #1 installation | Riky/Sunanto | 2026-06-01 | 2026-06-30 | 30 | 80% | In Progress | Trial Pocapick
Visual Bench #2 installation | Riky/Sunanto | 2026-06-01 | 2026-06-30 | 30 | 80% | In Progress | Trial Pocapick
Line-Relayout | Riky | 2026-06-15 | 2026-06-20 | 6 | 100% | Done
Electrical Wiring & Setup | Riky | 2026-06-15 | 2026-06-20 | 6 | 100% | Done
5. TESTING & QUALIFICATION
Manual bench Qualification | Riky/Sunanto/Irwan | 2026-06-23 | 2026-06-26 | 4 | 0% | Planned
SPEA T100 ICT program debug | Test Eng | 2026-06-24 | 2026-06-26 | 3 | 30% | In Progress
First-article inspection (FAI) | QA | 2026-06-29 | 2026-07-02 | 4 | 0% | Planned
PFMEA Update | Irwan | 2026-06-22 | 2026-07-04 | 13 | 20% | In Progress
Capacity Measurement by MTM | Funny | 2026-06-30 | 2026-07-02 | 3 | 0% | Planned
Qualification SPEA | All Team | 2026-06-29 | 2026-07-02 | 4 | 0% | Planned
6. TRAINING & HANDOVER
Operator training – Manual Bench | Trainee | 2026-07-01 | 2026-07-01 | 1 | 0% | Planned
Operator training – SPEA T100 | SPEA / Eng | 2026-07-01 | 2026-07-01 | 1 | 0% | Planned
SOP / WI documentation | Riky | 2026-07-01 | 2026-07-01 | 1 | 0% | Planned
Handover to Production | All Team | 2026-07-10 | 2026-07-14 | 5 | 0% | Planned
Project closure report | All Team | 2026-07-10 | 2026-07-14 | 5 | 0% | Planned
🏁 LINE GO-LIVE | All
Formulas:
DONE = IF(OR([OPEN]="",D8=""),"",IF(F8>=1,"Done",IF(AND(D8<TODAY(),F8<1),"Delayed",IF(F8>0,"In Progress","Planned"))))

## Example
PROJECT MANAGEMENT — GANTT CHART
Project Start Date (Mon): | 2026-06-01 | Today: | 2026-06-24 |  | Legend: |  |  | Done |  | In Progress |  | Planned |  | Delayed |  | Today
TOTAL ACTION |  | OPEN |  | IN PROGRESS |  | DONE |  | DELAYED |  |  |  | % COMPLETION
12 |  | 5 |  | 2 |  | 2 |  | 3 |  |  |  | 33.33%
Task / Milestone | Owner | Start Date | End Date | Duration (days) | % Done | Status | Project Update | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36 | WK37 | WK38 | WK39 | WK40 | WK41 | WK42 | WK43 | WK44 | WK45 | WK46 | WK47 | WK48 | WK49 | WK50 | WK51 | WK52
[7 empty] | Week starting → | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21
1. PLANNING
Project kick-off | All Team | 2026-06-01 | 2026-06-01 | 1 | 100% | Done
Define scope & objectives | PM | 2026-06-01 | 2026-06-05 | 5 | 100% | Done
Resource & budget plan | PM & Lead | 2026-06-04 | 2026-06-10 | 7 | 70% | Delayed
Risk assessment | PM | 2026-06-06 | 2026-06-12 | 7 | 50% | Delayed
2. EXECUTION
Setup workstations | Engineering | 2026-06-08 | 2026-06-18 | 11 | 40% | Delayed
Procure materials | Procurement | 2026-06-08 | 2026-06-26 | 19 | 30% | In Progress
Equipment commissioning | Engineering | 2026-06-18 | 2026-07-02 | 15 | 10% | In Progress
Operator training | HR & Lead | 2026-06-26 | 2026-07-09 | 14 | 0% | Planned
Pilot production run | Production | 2026-07-02 | 2026-07-16 | 15 | 0% | Planned
3. TESTING & GO-LIVE
Quality validation | QA | 2026-07-16 | 2026-07-23 | 8 | 0% | Planned
Documentation & SOPs | PM | 2026-07-09 | 2026-07-23 | 15 | 0% | Planned
Final sign-off | Sponsor | 2026-07-23 | 2026-07-23 | 1 | 0% | Planned
Formulas:
DONE = IF(OR([OPEN]="",D8=""),"",IF(F8>=1,"Done",IF(AND(D8<TODAY(),F8<1),"Delayed",IF(F8>0,"In Progress","Planned"))))